Spring Breaks ‘R’ Us (SBRU) Travel Service

Purpose Statement: The purpose of the SBRU team is to enhance the travel service experience for college students during spring break by providing affordable, enjoyable, and safe travel options.

Mission Statement: To simulate a real-world scenario to create and present various systems within the SBRU case study, using information and technologies we have learnt over the course of the semester.

Team Objectives:

- Completion of all parts of assignment 3 within the allocated time frame.

Team Members and Roles:

- Task 1: Gideon Nyamuame

- Task 2 and 3: Twinkle Mishra

- Team Charter and Presentation: Arashdeep Kaur

Communication Plan:

- Daily Check-ins: from the 11th of July 14, 2024 until assignment submission.

- Communication Tools: WhatsApp, Microsoft Teams.

Decision-Making Process: Consensus approach with team members. Majority deciding the direction we take.

Conflict Resolution: Solve any issues in-house. If a resolution cannot be achieved, we send an email to the professor to see next steps.

Resources and Support:

- Econestoga System Analysis and Design in a changing world.

- Technology: Visual Paradigm.

Milestones and Timeline:

- 11/07/2024: Gideon and Twinkle will finish up a first draft of their respective sections

- 12/07/204: Team meeting to fill in any gaps Arashdeep might have to work on her presentation.

- 14/07/2024: Gideon and Twinkle submit final draft of work.

- 15/07/2024: Mock presentation and final edits.

Performance Metrics:

Feedback from the professor and our peers. Did they understand the presentation? Were we able to answer any questions that were raised? Were the presented documents and diagrams understandable to the professor, and lastly the evaluation given to us by the professor.